## Document Info
KONTRUCKTORS SA Risk Register and Risk Treatment Plan KSA-RM-001 ¦ Version 1.0 ¦ Confidential
Document Reference | KSA-RM-001
Version | 1.0
Classification | Confidential
Effective Date | 15 September 2026
Review Date | 15 September 2027
Document Owner | Information Security Manager
Approved By | Chief Executive Officer
Related Documents | KSA-ISP-002 Information Security Policy; KSA-ISP-AUP-001 Acceptable Use Policy
Risk Appetite Statement | Kontrucktors SA accepts LOW residual risk. MEDIUM risk requires treatment plan. HIGH and CRITICAL risk require immediate action and CEO approval to accept.
RISK SCORING MATRIX
Likelihood x Impact = Risk Score
Likelihood 1: Rare | Impact 1: Negligible
Likelihood 2: Unlikely | Impact 2: Minor
Likelihood 3: Possible | Impact 3: Moderate
Likelihood 4: Likely | Impact 4: Major
Likelihood 5: Almost Certain | Impact 5: Critical
Score 1-4: LOW | Score 5-9: MEDIUM
Score 10-16: HIGH | Score 17-25: CRITICAL

## Risk Register
KONTRUCKTORS SA ¦ Risk Register ¦ KSA-RM-001 ¦ Version 1.0 ¦ Confidential
Risk ID | Asset / Process | Risk Description | Threat / Vulnerability | Risk Category | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Risk Rating | Existing Controls | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Rating | Treatment Option | Risk Owner
R-001 | Customer Contract Database | Unauthorised access to customer leasing and sales contracts containing personal and financial data | Weak access controls; absence of MFA for internal systems | Data Protection / FADP | 3 | 5 | 15 | High | Basic username/password authentication; network firewall in place | 2 | 4 | 8 | Medium | Reduce | IT Manager
R-002 | Employee Laptops (All Offices) | Loss or theft of company laptop containing unencrypted confidential data in field operations | Physical theft; remote work; lack of full-disk encryption enforcement | Physical / Asset Management | 4 | 4 | 16 | High | Asset tracking register maintained; IT support available | 2 | 3 | 6 | Medium | Reduce | IT Manager
R-003 | Email Systems | Phishing attack resulting in compromise of employee credentials and access to company systems | Social engineering; lack of security awareness training | Cyber / Human Factor | 4 | 4 | 16 | High | Spam filter in place; basic IT policy communicated at onboarding | 2 | 3 | 6 | Medium | Reduce | Information Security Manager
R-004 | Fleet Management System | Ransomware infection encrypting fleet scheduling and maintenance records, halting operations | Unpatched software; no endpoint detection and response (EDR) tooling | Cyber / Operational | 3 | 5 | 15 | High | Antivirus software on workstations; periodic manual backups | 2 | 4 | 8 | Medium | Reduce | IT Manager
R-005 | Supplier Integrations | Third-party supplier with access to company systems suffers a breach, exposing Kontrucktors SA data | Insufficient supplier security assessment; no contractual security obligations | Third Party / Supply Chain | 3 | 4 | 12 | High | Standard contracts in place; no formal security assessment conducted | 2 | 3 | 6 | Medium | Reduce | Information Security Manager
R-006 | HR and Payroll System | Insider threat: disgruntled or departing employee exfiltrates sensitive HR or payroll data | Insufficient offboarding procedures; excessive access rights retained post-departure | Insider Threat / HR | 2 | 5 | 10 | High | Informal offboarding checklist; HR notifies IT on departure | 1 | 4 | 4 | Low | Reduce | HR Manager
R-007 | Cloud Storage (All Locations) | Misconfiguration of cloud storage bucket exposes internal documents to the public internet | Lack of cloud security expertise; no cloud configuration review process | Cloud / Configuration | 3 | 4 | 12 | High | Cloud provider default settings applied; no formal review | 2 | 3 | 6 | Medium | Reduce | IT Manager
R-008 | Office Networks (Geneva, Lausanne, Zurich, Lugano) | Unauthorised physical access to office network infrastructure enabling network interception | Unsecured server rooms; visitor access not consistently controlled | Physical / Network | 2 | 4 | 8 | Medium | Reception sign-in for visitors; basic door lock on server room | 1 | 3 | 3 | Low | Reduce | Facilities Manager
R-009 | Business Operations (All) | Extended system outage due to power failure or infrastructure incident at any office location | Single points of failure; no formal business continuity or disaster recovery plan | Availability / Business Continuity | 3 | 4 | 12 | High | UPS units in Geneva office only; manual workarounds possible for short outages | 2 | 3 | 6 | Medium | Reduce | CEO
R-010 | GDPR and FADP Compliance | Regulatory breach resulting in fines and reputational damage due to non-compliance with FADP or GDPR | Incomplete data mapping; no formal Data Protection Officer appointed; no breach notification procedure | Legal / Regulatory | 2 | 5 | 10 | High | Legal counsel engaged on an ad hoc basis; basic privacy notices published | 1 | 4 | 4 | Low | Reduce | Information Security Manager
R-011 | Customer Portal / Website | Web application vulnerability exploited to access customer account data or inject malicious content | Absence of regular penetration testing; no web application firewall | Cyber / Application | 3 | 4 | 12 | High | Hosting provider applies standard protections; no custom security testing | 2 | 3 | 6 | Medium | Reduce | IT Manager
R-012 | Finance and Billing Systems | Fraudulent invoice manipulation or payment redirection through compromise of finance systems | Business email compromise; insufficient payment verification controls | Financial / Fraud | 2 | 5 | 10 | High | Dual authorisation for large payments; finance team awareness informal | 1 | 4 | 4 | Low | Reduce | Finance Director
R-013 | All Information Systems | Failure to detect a security breach due to absence of security monitoring and logging | No SIEM or centralised log management; no 24/7 monitoring capability | Cyber / Detection | 4 | 4 | 16 | High | Individual system logs available but not centralised or reviewed | 3 | 4 | 12 | High | Reduce | IT Manager
R-014 | Password Management (All Users) | Account compromise through weak, reused, or shared passwords across systems | No enforced password policy; no password manager deployed company-wide | Cyber / Authentication | 4 | 3 | 12 | High | IT policy states password requirements but enforcement is manual | 2 | 2 | 4 | Low | Reduce | IT Manager
R-015 | Office Premises (All Locations) | Damage to IT equipment and data due to fire, flood, or other physical disaster at office location | No off-site backup for all locations; geographic concentration of infrastructure | Physical / Environmental | 2 | 5 | 10 | High | Insurance in place; Geneva office has off-site backup only | 2 | 3 | 6 | Medium | Reduce/Transfer | CEO

## Risk Treatment Plan
KONTRUCKTORS SA ¦ Risk Treatment Plan ¦ KSA-RM-001 ¦ Version 1.0 ¦ Confidential
Risk ID | Risk Description (Summary) | Residual Risk Rating | Treatment Actions | ISO 27001:2022 Control Reference | Responsible Owner | Target Completion Date | Status | Notes
R-001 | Unauthorised access to customer contract database | High | 1. Enforce MFA on all internal systems 2. Implement role-based access control (RBAC) 3. Conduct quarterly access reviews 4. Enable audit logging on database access | A.8.2, A.8.3, A.8.4, A.8.15 | IT Manager | 31 Oct 2026 | In Progress | RBAC model to be designed by IT in October
R-002 | Loss or theft of unencrypted laptop | Medium | 1. Enforce full-disk encryption (BitLocker/FileVault) on all devices 2. Enrol all devices in MDM 3. Implement remote wipe capability 4. Update asset register | A.7.9, A.8.1, A.8.3 | IT Manager | 15 Oct 2026 | In Progress | MDM tool evaluation underway
R-003 | Phishing attack compromising credentials | Medium | 1. Deploy company-wide security awareness training 2. Conduct simulated phishing exercise 3. Enable advanced email filtering 4. Enforce MFA on all email accounts | A.6.3, A.8.6, A.8.23 | Information Security Manager | 30 Nov 2026 | Planned | Training provider to be selected by October
R-004 | Ransomware encrypting fleet management system | High | 1. Deploy EDR solution on all endpoints 2. Implement automated daily backups with off-site copy 3. Test backup restoration quarterly 4. Apply OS and application patches within 14 days of release | A.8.7, A.8.8, A.8.13 | IT Manager | 31 Oct 2026 | In Progress | EDR vendor shortlisted; backup procedure in draft
R-005 | Third-party supplier breach exposing company data | Medium | 1. Implement supplier security assessment process 2. Include security obligations in all supplier contracts 3. Maintain approved supplier register 4. Require breach notification clauses in all DPAs | A.5.19, A.5.20, A.5.22 | Information Security Manager | 30 Nov 2026 | Planned | Standard supplier security questionnaire to be drafted
R-006 | Insider threat: data exfiltration by departing employee | Medium | 1. Formalise offboarding checklist with immediate access revocation 2. Implement HR-IT notification SLA of same business day 3. Conduct exit interviews including data return confirmation 4. Review access rights monthly for role changes | A.6.5, A.8.2, A.8.3 | HR Manager | 31 Oct 2026 | Planned | Offboarding procedure to be drafted jointly by HR and IT
R-007 | Cloud storage misconfiguration | Medium | 1. Conduct cloud security configuration review 2. Enable cloud security posture management (CSPM) tooling 3. Apply least-privilege to all cloud storage buckets 4. Schedule quarterly cloud configuration audits | A.8.9, A.8.10, A.5.23 | IT Manager | 30 Nov 2026 | Planned | Cloud audit to be scoped in October
R-008 | Unauthorised physical access to network infrastructure | Low | 1. Install access-controlled locks on all server rooms at all four offices 2. Implement visitor management log across all locations 3. Review physical access rights quarterly | A.7.1, A.7.2, A.7.3 | Facilities Manager | 31 Dec 2026 | Planned | Physical security assessment to be conducted per office
R-009 | Extended system outage due to infrastructure failure | Medium | 1. Develop and document Business Continuity Plan 2. Deploy UPS to Lausanne, Zurich, and Lugano offices 3. Define RTO and RPO for all critical systems 4. Conduct annual BCP tabletop exercise | A.5.29, A.5.30, A.8.13 | CEO | 28 Feb 2027 | Planned | BCP project to be initiated Q4 2026
R-010 | GDPR/FADP regulatory breach | Medium | 1. Complete personal data mapping exercise across all offices 2. Appoint or designate Data Protection contact 3. Develop breach notification procedure 4. Conduct annual FADP/GDPR compliance review | A.5.31, A.5.34 | Information Security Manager | 31 Jan 2027 | Planned | Data mapping to commence October 2026
R-011 | Web application vulnerability exploitation | Medium | 1. Commission annual penetration test of customer portal 2. Deploy web application firewall (WAF) 3. Implement secure development guidelines 4. Review third-party hosting provider SLAs | A.8.8, A.8.25, A.8.26 | IT Manager | 31 Jan 2027 | Planned | Penetration test to be budgeted for Q1 2027
R-012 | Fraudulent invoice manipulation | Medium | 1. Formalise dual-authorisation policy for all payments above CHF 10,000 2. Implement supplier bank account change verification procedure 3. Conduct finance team security awareness session | A.5.15, A.8.22 | Finance Director | 31 Oct 2026 | Planned | Payment control procedure to be drafted by Finance
R-013 | Failure to detect security breach (no monitoring) | High | 1. Implement centralised log management solution 2. Define log retention period of minimum 12 months 3. Establish security event review process (weekly minimum) 4. Evaluate SIEM solution for future deployment | A.8.15, A.8.16, A.8.17 | IT Manager | 28 Feb 2027 | Planned | Log management solution to be selected Q4 2026
R-014 | Account compromise through weak passwords | Low | 1. Enforce password policy via Active Directory Group Policy 2. Deploy company-wide password manager 3. Block commonly used and breached passwords 4. Enforce MFA as primary control | A.8.2, A.8.5 | IT Manager | 15 Oct 2026 | In Progress | Password manager evaluation complete; deployment planned
R-015 | Physical disaster at office location | Medium | 1. Implement off-site backup for all four office locations 2. Document disaster recovery procedure per site 3. Test recovery from backup quarterly 4. Review insurance coverage adequacy | A.7.4, A.7.5, A.8.13 | CEO | 28 Feb 2027 | Planned | Off-site backup to be extended to Lausanne, Zurich, Lugano in Q4

## Risk Heat Map
KONTRUCKTORS SA ¦ Risk Heat Map ¦ Inherent Risk Ratings
LIKELIHOOD | IMPACT
| 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Critical
5 Almost Certain | MEDIUM Score: 5 | HIGH Score: 10 | HIGH Score: 15 | CRITICAL Score: 20 | CRITICAL Score: 25
4 Likely | LOW Score: 4 | MEDIUM Score: 8 | HIGH Score: 12 | HIGH Score: 16 | CRITICAL Score: 20
3 Possible | LOW Score: 3 | MEDIUM Score: 6 | MEDIUM Score: 9 | HIGH Score: 12 | HIGH Score: 15
2 Unlikely | LOW Score: 2 | LOW Score: 4 | MEDIUM Score: 6 | MEDIUM Score: 8 | HIGH Score: 10
1 Rare | LOW Score: 1 | LOW Score: 2 | LOW Score: 3 | LOW Score: 4 | MEDIUM Score: 5
RISK PLACEMENT ON HEAT MAP
Risk ID | Asset/Process | Likelihood | Impact | Score | Inherent Rating | Treatment
R-001 | Customer Contract DB | 3 | 5 | 15 | High | R
R-002 | Employee Laptops | 4 | 4 | 16 | High | R
R-003 | Email / Phishing | 4 | 4 | 16 | High | R
R-004 | Fleet System Ransomware | 3 | 5 | 15 | High | R
R-005 | Supplier Breach | 3 | 4 | 12 | High | R
R-006 | Insider Threat | 2 | 5 | 10 | High | R
R-007 | Cloud Misconfiguration | 3 | 4 | 12 | High | R
R-008 | Physical Network Access | 2 | 4 | 8 | Medium | R
R-009 | System Outage | 3 | 4 | 12 | High | R
R-010 | GDPR/FADP Breach | 2 | 5 | 10 | High | R
R-011 | Web App Vulnerability | 3 | 4 | 12 | High | R
R-012 | Invoice Fraud | 2 | 5 | 10 | High | R
R-013 | No Security Monitoring | 4 | 4 | 16 | High | R
R-014 | Weak Passwords | 4 | 3 | 12 | High | R
R-015 | Physical Disaster | 2 | 5 | 10 | High | R